## Foglio1
Project Plan
First Phase: EndUser
Activity | Beginning of the activity | Duration of the activity | Time (expressed in days)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
DataBaseHandler Implementation | 1 | 4 | bar: Time (expressed in days) 1 to Time (expressed in days) 4
UserAccessHandler Implementation | 2 | 3 | bar: Time (expressed in days) 2 to Time (expressed in days) 4
EndUserHandler Implementation | 2 | 3 | bar: Time (expressed in days) 2 to Time (expressed in days) 4
EndUserApplication Implementation | 3 | 6 | bar: Time (expressed in days) 3 to Time (expressed in days) 8
DataBaseHandler and DataBase service Integration | 5 | 2 | bar: Time (expressed in days) 5 to Time (expressed in days) 6
UserAccessHandler, EndUserHandler, DataBaseHandler Integration | 5 | 3 | bar: Time (expressed in days) 5 to Time (expressed in days) 7
EndUserApplication, UserAccessHandler, EndUserHandler Integration | 8 | 3 | bar: Time (expressed in days) 9 to Time (expressed in days) 11
Single units testing | 5 | 7 | bar: Time (expressed in days) 5 to Time (expressed in days) 11
First Phase Testing | 11 | 5 | bar: Time (expressed in days) 12 to Time (expressed in days) 16
Second Phase: Authority
Activity | Beginning of the activity | Duration of the activity | Time (expressed in days) 1: Time (expressed in days)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
DataBaseHandler Implementation | 1 | 2 | bar: Time (expressed in days) 1 to Time (expressed in days) 2
UserAccessHandler Implementation | 2 | 2 | bar: Time (expressed in days) 2 to Time (expressed in days) 3
AuthorityHandler Implementation | 2 | 4 | bar: Time (expressed in days) 2 to Time (expressed in days) 5
EndUserHandler Implementation | 5 | 2 | bar: Time (expressed in days) 5 to Time (expressed in days) 6
AuthorityApplication Implementation | 2 | 7 | bar: Time (expressed in days) 2 to Time (expressed in days) 8
DataBaseHandler and DataBase service Integration | 3 | 1 | bar: Time (expressed in days) 3
UserAccessHandler, AuthorityHandler, DataBaseHandler Integration | 6 | 3 | bar: Time (expressed in days) 6 to Time (expressed in days) 8
AuthorityHandler and EndUserHandler inegration | 7 | 2 | bar: Time (expressed in days) 7 to Time (expressed in days) 8
AuthorityApplication, UserAccessHandler, AuthorityrHandler Integration | 9 | 3 | bar: Time (expressed in days) 9 to Time (expressed in days) 11
Single units testing | 3 | 9 | bar: Time (expressed in days) 3 to Time (expressed in days) 11
Second Phase Testing | 12 | 5 | bar: Time (expressed in days) 12 to Time (expressed in days) 16
Third Phase: Statistics
Activity | Beginning of the activity | Duration of the activity | Time (expressed in days) 1: Time (expressed in days)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
DataBaseHandler Implementation | 1 | 2 | bar: Time (expressed in days) 1 to Time (expressed in days) 2
StatisticsHandler Implementation | 2 | 5 | bar: Time (expressed in days) 2 to Time (expressed in days) 6
AuthorityHandler Implementation | 4 | 2 | bar: Time (expressed in days) 4 to Time (expressed in days) 5
EndUserHandler Implementation | 4 | 2 | bar: Time (expressed in days) 4 to Time (expressed in days) 5
AuthorityApplication Implementation | 6 | 4 | bar: Time (expressed in days) 6 to Time (expressed in days) 9
EndUserApplication Implementation | 8 | 2 | bar: Time (expressed in days) 8 to Time (expressed in days) 9
DataBaseHandler and DataBase service Integration | 3 | 2 | bar: Time (expressed in days) 3 to Time (expressed in days) 4
StatisticsHandler, DataBaseHandler Integration | 7 | 2 | bar: Time (expressed in days) 7 to Time (expressed in days) 8
AuthorityHandler, EndUserHandler, StatisticsHandler Integration | 7 | 3 | bar: Time (expressed in days) 7 to Time (expressed in days) 9
StatisticsHandler and Map services integration | 7 | 5 | bar: Time (expressed in days) 7 to Time (expressed in days) 11
AuthorityApplication and AuthorityrHandler Integration | 10 | 2 | bar: Time (expressed in days) 10 to Time (expressed in days) 11
EndUserApplication and EndUserHandler Integration | 10 | 2 | bar: Time (expressed in days) 10 to Time (expressed in days) 11
Single units testing | 3 | 9 | bar: Time (expressed in days) 3 to Time (expressed in days) 11
Third Phase Testing | 12 | 5 | bar: Time (expressed in days) 12 to Time (expressed in days) 16
Fourth Phase: Municipality
Activity | Beginning of the activity | Duration of the activity | Time (expressed in days) 1: Time (expressed in days)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
DataBaseHandler Implementation | 1 | 2 | bar: Time (expressed in days) 1 to Time (expressed in days) 2
UserAccessHandler Implementation | 2 | 2 | bar: Time (expressed in days) 2 to Time (expressed in days) 3
MunicipalityHandler Implementation | 3 | 4 | bar: Time (expressed in days) 3 to Time (expressed in days) 6
MunicipalitySoftware Implementation | 2 | 7 | bar: Time (expressed in days) 2 to Time (expressed in days) 8
DataBaseHandler and DataBase service Integration | 3 | 2 | bar: Time (expressed in days) 3 to Time (expressed in days) 4
UserAccessHandler, DataBaseHandler Integration | 4 | 3 | bar: Time (expressed in days) 4 to Time (expressed in days) 6
StatisticsHandler, MunicipalityHandler, DataBaseHandler Integration | 7 | 3 | bar: Time (expressed in days) 7 to Time (expressed in days) 9
MunicipalitySoftware and MunicipalityHandler Integration | 9 | 3 | bar: Time (expressed in days) 9 to Time (expressed in days) 11
Single units testing | 3 | 9 | bar: Time (expressed in days) 3 to Time (expressed in days) 11
Fourth Phase Testing | 12 | 5 | bar: Time (expressed in days) 12 to Time (expressed in days) 16